## Project_Costs
Mock Project Cost and Schedule Control
Budget vs actual and forecast exercise workbook
Work Package | Owner | Budget (RM) | Actual (RM) | Forecast to Complete (RM) | Schedule Status | Risk Rating | Variance (RM) | Copilot Exercise
Data ingestion | Data Engineering | 104087 | 88927 | 70910 | Delayed | High |  | Explain the largest unfavorable cost variances.
KPI dictionary | Governance | 132580 | 124349 | 54092 | On track | Medium |  | Create a forecast completion summary by work package.
Dashboard build | Performance | 156536 | 110200 | 33834 | Watch | Low |  | Build a traffic-light project dashboard.
Security review | Cyber | 91507 | 92725 | 54608 | Watch | High |  | Draft management recommendations with clear decisions needed.
Change and training | PMO | 136905 | 97422 | 11330 | Delayed | Low
Pilot support | Operations | 56221 | 88270 | 63271 | Watch | High